## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: Bang! |  |  |  |  | Rami Masoud | rmasou2@uic.edu
Week Of: 4/26/19 |  |  |  |  | Nathan Loo | nloo2@uic.edu
[5 empty] | Aaron Lau | alau8@uic.edu
[5 empty] | Andrew Wirtz | awirtz@uic.edu
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
Create classes which will be part of the server program | 1 | Nathan Loo | Create the Classes, Instance Variables, and the methods | Add more classes that fit and modify existing classes | Make sure the class implementations work within the evaluation method | Our project changed from last week, so anything we have already done prior might need to be modified so it works with our new game
Create a 4 player client server connection | 2 | Rami Masoud | Utilize java sockets, creating a new thread for each of the players connected. Notify players on who's connected. | Implement a GUI, creating different scenes for the server. Starting Scene, Online Scene | Implement the actual game such as where people actually sit
Create a GUI for the gameplay window for the clients | 3 | Andrew Wirtz | Create a scene to display a current player's cards. The last card thrown. The other players. Number of cards in each hand. | Create on-action methods within the client program which will adhere to the JavaFX items created the week before. | Put in the pictures, make sure people are seated based on how the server seats them
Brain storm on a possible way which will evaluate the game and the actions of the clients. | 4 | Aaron Lau | Conceptualize the game rules, perhaps write down some sudo code as a rough draft for the methods. | Start implementing the game evaluation, this will be done by using the Class implementation created the week before. | Implement the game logic server side, using the classes created by Nathan and translate seudo code. Implement how the server and client will talk throughout the game, and build a basic talking functionality for the game.