## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: Bang! |  |  |  |  | Rami Masoud | rmasou2@uic.edu
Week Of: 4/28/19 |  |  |  |  | Nathan Loo | nloo2@uic.edu
[5 empty] | Aaron Lau | alau8@uic.edu
[5 empty] | Andrew Wirtz | awirtz@uic.edu
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
Create classes which will be part of the server program | 1 | Nathan Loo | Create the Classes, Instance Variables, and the methods. Add more classes that fit and modify existing classes Make sure the class implementations work within the evaluation method | Worked on combining the Game classes with the server. For example, we have already started creating an output for each players hand that will be sent from the server to the designated client. | Meet with the group on Monday and work on the project. Further test out the game, make sure that the game rules are properly functioning | Our project changed from last week, so anything we have already done prior might need to be modified so it works with our new game. ....... Also, In order to work efficently on our project we need to work together in a group, so we can better understand each group members contributions and combine the project together.
Create a 4 player client server connection | 2 | Rami Masoud | Utilize java sockets, creating a new thread for each of the players connected. Notify players on who's connected. Created function to make sure that the ports properly closed for each client. | Along with Nathan I combined the game classes along with the Client/Server program. While Nathan knows more about the game classes, I helped out to make sure that sure that the server is properly outputting to each client/ | Meet with the group on Monday and work on the project. Combine the player array from the server with the player array list from the game classes.
Create a GUI for the gameplay window for the clients | 3 | Andrew Wirtz | Create a scene to display a current player's cards. The last card thrown. The other players. Number of cards in each hand. | Create on-action methods within the client program which will adhere to the JavaFX items created the week before. | Meet with the group on Monday and work on the project. Combine the JavaFX gui with the client server. Work on making buttons to represent the cards, and the text that the client will send to the server which will be parsed later on.
Brain storm on a possible way which will evaluate the game and the actions of the clients. | 4 | Aaron Lau | Conceptualize the game rules, perhaps write down some sudo code as a rough draft for the methods. | Start implementing the game evaluation, this will be done by using the Class implementation created the week before. | Implement the game logic server side, using the classes created by Nathan and translate seudo code. Implement how the server and client will talk throughout the game, and build a basic talking functionality for the game.