## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: 4 Player UNO Implementation |  |  | First Sprint Sheet Created for Project 5 |  | Rami Masoud | rmasou2@uic.edu
Week Of: Friday April 19, 2019 |  |  |  |  | Nathan Loo | nloo2@uic.edu
[5 empty] | Aaron Lau | alau8@uic.edu
[5 empty] | Andrew Wirtz | awirtz5@uic.edu
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
Create card, deck, player classes which will be a part of the server program. | 1 | Nathan Loo | N/A | Work on each of the classes by creating their variables and methods. | Make sure the Class implementations work within the evaluation method.
Create a 4 player client server connection. | 2 | Rami Masoud | N/A | Utilize java sockets, creating a new thread for each of the players connected. Notify players on who's connected. | Implement a GUI, creating different scenes for the server. Starting Scene, Online Scene
Create a GUI for the gameplay window for the Clients. | 3 | Andrew Wirtz | N/A | Create a scene to display a current player's cards. The last card thrown. The other players. Number of cards in each hand. | Create on-action methods within the client program which will adhere to the JavaFX items created the week before.
Brain storm on a possible way which will evaluate the game and the actions of the clients. | 4 | Aaron Lau | N/A | Conceptualize the game rules, perhaps write down some sudo code as a rough draft for the methods. | Start implementing the game evaluation, this will be done by using the Class implementation created the week before.